## Tasks
Kappa Tasks
|  | Select Version: |  |  | Total (h) | Total (d) | Open (h) | Open (d) |  | Tasks | 0
|  | 0.1 |  | Estimation | 1 | 1h | 1 | 1h | Open | 4
|  |  |  | Effort | 0 | 0h |  |  | Closed | 7
|  | h/day | [6 empty] | Total | 11
|  | 8 |  | Est. Done | 0%
|  |  | target version | actual version |  | in h | in h
Issue No. | Domain | Due Date | Version | Implemented | Responsible | Estimation | Effort | Type | Priority | Status | Issue | Description | Comment
20260505-1 |  |  | 0.1 |  | huebi | 1 | 0 | Feature | High | OPEN | pointer params
20260505-2 |  |  | 0.1 |  | huebi |  |  | Feature | High | CLOSED | multiple definitions | var x,y,z: int
|  |  | 0.1 | [6 empty] | CLOSED | clear() to clear an array
|  |  | 0.1 | [6 empty] | OPEN | play a sound file
|  |  | 0.1 | [6 empty] | OPEN | read from a file on disk
|  |  | 0.1 | [6 empty] | OPEN | communication to internet | connect, send, recv, disconnect, available
|  |  | 0.1 |  |  |  |  | Investigation | High | CLOSED | function we don’t need are not in PRG
|  |  | 0.1 |  |  |  |  | Feature | High | CLOSED | Screen funcs | cls(), put(), puts().
|  |  | 0.2 |  |  |  |  | Feature | High | OPEN | Dynamic Arrays | make() creates a dynamic sized array.
|  |  | 0.1 |  |  |  |  | Improvement | High | CLOSED | Strings are not 0 terminated anymore | strings are arrays and arrays have capacity and length
|  |  | 0.1 |  |  |  |  | Feature | High | CLOSED | println() | print + CRLF/LF (13)
|  |  | 0.1 |  |  |  |  | Feature | High | CLOSED | 0xXXX support | add Hexnumber prefix 0x
20260524-1 |  |  | 1.0 |  | huebi |  |  | Feature | High | OPEN | for loop
20260524-2 |  |  | 1.0 |  | huebi |  |  | Feature | Medium | OPEN | select | check if a GO-like select is better than a lot of if then else

## Statistics
Version | 0.1
|  |  | Date | Estimation
|  | Start | 2026-05-05 | 1 |  |  | In order to maintain the statistics do this:
|  | Finished | #DIV/0! | 0 |  |  | Select in the Tasks sheet the right Version. Then switch to statistics sheet. You see the Open and Closed Tasks.
Create in the table a new entry. Yes this is manual copy and paste but we do not need macros in that case, which keeps the excel simple!
|  |  | Today | Open | #TotalTasks | #OpenTasks
|  |  | 2026-05-24 | 1 | 11 | 4
|  |  | Date | Estimation | Tasks | OpenTasks
|  |  | 2026-05-05 | 1 | 1 | 1

## Settings
Status | Version | Type | Priority | day in h: | 8
OPEN | 0.1 | Bug | High
CLOSED | 0.2 | Improvement | Medium
CRITICAL | 1.0 | Test | Low
ACTIVE | 2.0 | Documentation
Feature
Investigation
Feedback